## TODO
Topic | Priority | Status | Time spent
Player
Find spritesheet | High | Finished | 0h
spitesheet ready to use | High | Finished | 0h
Player class
function Die | High | Finished | 0.5h
function IsHit | High | Finished | 3h
Movement | High | Finished | 4h
Item
spitesheet ready to use | High | Finished | 0h
Find spritesheet | High | Finished | 0h
Item manager | Medium | Finished | 1h
Item class
Make interactable | Medium | Finished | 2h
Create equipables | Medium | Finished | 3h
Enemy
Find spritesheet | High | Finished | 0h
spitesheet ready to use | High | Finished | 0h
Create boss | Medium | Finished | 2h
Enemy class
Basic movement | High | Finished | 2h
Collision | High | Finished | 3h
Pathfinding | Medium | Finished | 10h
Fx manager
Display damage | Medium | Finished | 15h
Display exp | Medium | Finished | 1h
Sound manager
Menu music | Medium | Finished | 2h
Game music | Medium | Finished | 1h
Sound effects | Medium | Finished | 0.5h
Volume controls | Medium | Finished | 0.5h
Inventory
Create texture | Medium | Finished | 2h
Manage items | Medium | Finished | 4h
Make equip, drop | Medium | Finished | 2h
Inventory Tiles
Make fillable with item | Medium | Finished | 3h
User Interface
Showstats (health, exp) | Medium | Finished | 4h
Make usable buttons | Medium | Finished | 2h
Camera
Following player | High | Finished | 2h
Map Camera
Free moving | Medium | Finished | 1h
Zooming | Medium | Finished | 2h
Menu
Play button | Medium | Finished | 0.5h
menu animation | Low | Finished | 1h
Level editor
Map editor
Make save-able | High | Finished | 2h
Tile Manager
Draw level | High | Finished | 6h
Save/Load tiles | High | Finished | 2h
Tile class
Make a grid based system | High | Finished | 4h
Differentiate walkable | High | Finished | 4h
Enemy editor
Add enemies | Low | Finished | 2h
Camera
Camera movement | High | Finished | 2h